## Backlog
User Story | Estimated Complexity | Priority
<<Staff>> can log in using their Staff ID | 3
8
<<Staff>> logging in should be shown <<Quiz Overview>> | 2 | 4
<<Staff>> can select a quiz listed on <<Quiz Overview>> | 1 | 4
<<Staff>> can quick-access create a quiz from <<Quiz Overview>> | 1 | 4
<<Staff>> can quick-access edit a quiz from <<Quiz Overview>> | 1 | 4
<<Staff>> can create a quiz from <<Quiz Overview>> | 3
4
<<Staff>> can quick-access edit a quiz from <<View Individual Quiz>> | 1 | 2
<<Staff>> can choose a module to associate with a quiz from <<Edit Quiz>> | 2 | 2
<<Staff>> can input the title of a quiz from <<Edit Quiz>> | 1 | 2
<<Staff>> can add questions to a quiz from <<Edit Quiz>> | 3 | 2
<<Staff>> can add multiple answers to a question from <<Edit Quiz>> | 2 | 2
<<Staff>> can choose which answer should be marked as correct from <<Edit Quiz>> | 3 | 2
<<Staff>> can add an explanation of a correct answer from <<Edit Quiz>> | 2 | 2
<<Staff>> can add an explanation of incorrect answers from <<Edit Quiz>> | 2 | 2
<<Staff>> can make a quiz available to students from <<Edit Quiz>> | 1 | 2
<<Staff>> can quick-access make quiz available from <<Quiz Overview>> | 1 | 4
<<Staff>> can quick-access make quiz available from <<View Individual Quiz>> | 1 | 2
<<Staff>> can quick-acess view overall results from <<View Individual Quiz>> | 1 | 2
<<Staff>> can sort quizzes on <<Quiz Overview>> by quizzes they have created | 2
2
<<Staff>> can see comprehensive information about a quiz from <<Quiz Summary - Staff View>> | 5
2
<<Staff>> can filter results on <<Quiz Summary - Staff View>> by date range and/or student | 4
1
<<Student>> can log in using their Matriculation ID | 3 | 8
<<Student>> after logging in should be shown <<Quiz Overview>> | 1 | 4
<<Student>> can see all modules from <<Quiz Overview>> | 2 | 2
<<Student>> can filter quizzes by module from <<Quiz Overview>> | 1 | 2
<<Student>> can filter quizzes by completion from <<Quiz Overview>> | 1 | 2
<<Student>> can select a quiz listed on <<Quiz Overview>> | 1 | 4
<<View Individual Quiz>> should display a list of multiple-choice questions | 3 | 4
<<Student>> can submit a quiz after completion on <<View Individual Quiz>> | 1 | 4
<<Quiz Summary - Student View>> should display all questions | 6
2
<<Student>> can see whether an answer is correct from <<Quiz Summary - Student View>> | 1 | 2
<<Student>> can see a total score on <<Quiz Summary - Student View>> | 1 | 2
<<Quiz Summary - Student View>> should display all given answers | 3 | 2
<<Quiz Summary - Student View>> should display an explanation for each correct answer where applicable | 1 | 2
<<Quiz Summary - Student View>> should display an explanation for each incorrect answer where applicable | 1 | 2
<<Student>> can see if a quiz is completed from <<Quiz Overview>> | 1 | 2
<<Staff>> can see the average score of all responses on <<Quiz Summary - Staff View>> | 1 | 2
<<Student>> can favourite a module from <<Quiz Overview>> | 1 | 1
<<Student>> can favourite a quiz from <<Quiz Overview>> | 1 | 1
<<Student>> can favourite a quiz from <<View Individual Quiz>> | 1 | 1
<<Student>> favourites should take precedence on <<Quiz Overview>> | 2 | 1
<<Student>> can see a summary of previously completed quizzes on <<Quiz Summary - Student View>> | 4 | 2
<<Student>> can print a summary from <<Quiz Summary - Student View>> | 2 | 4
<<Student>> can email a summary from <<Quiz Summary - Student View>> | 8
4

## Actors
<<Student>>
<<Staff>>
<<Quiz Overview>>
<<View Individual Quiz>>
<<Edit Quiz>>