## Sheet1
Team 5 - Sprint 2
User Story | Estimated Complexity | Done? | Tasks | Owner | Estimated Effort (Person hours) | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
1. <<Staff>> can log in using their Staff ID | 2 |  |  |  | 1
4
2
1
1
4
|  | N | Stored procedure for login details | Igors | 4
2. <<Staff>> logging in should be shown <<Quiz Overview>> | 2 |  |  |  | 2
1
3. <<Staff>> can select a quiz listed on <<Quiz Overview>> | 1 |  |  |  | 1
4. <<Staff>> can quick-access create a quiz from <<Quiz Overview>> | 1 |  |  |  | 1
5. <<Staff>> can quick-access edit a quiz from <<Quiz Overview>> | 1 |  |  |  | 1
6. <<Staff>> can create a quiz from <<Quiz Overview>> | 3 |  | Insert values to table | Dan | 3 | bar: Tue
2
1
1
1
1
7. <<Staff>> can choose a module to associate with a quiz from <<Edit Quiz>> | 1 | N | Links on quiz overview page | Finlay | 1
8. <<Staff>> can input the title of a quiz from <<Edit Quiz>> | 2 | N | Edit quiz page -> add textbox for title | Finlay | 2
|  |  | Ensure that new textbox submits values | Finlay | 1
9. <<Staff>> can input the module(s) a quiz should be categorised as from <<Edit Quiz>> | 1 | N | Edit quiz page -> add textbox for title | Finlay | 1
|  |  | Ensure that new textbox submits values | Finlay | 1
10. <<Staff>> can add questions to a quiz from <<Edit Quiz>> | 3 | N | Edit quiz page -> Create div that contains question name + textbox for answers | Finlay | 2
|  |  | Ensure that all divs submit correct values | Finlay | 2
11. <<Staff>> can add multiple answers to a question from <<Edit Quiz>> | 2 | N | Create buttons that add additional textboxes for answers | Finlay | 2
|  |  | Create button to add div with aforementioned functionality | Finlay | 2
12. <<Staff>> can choose which answer should be marked as correct from <<Edit Quiz>> | 3 | N | Create checkbox on all divs to indicate correct answer | Finlay | 1
|  |  | Ensure that checkbox submits values | Finlay | 2
13. <<Staff>> can add an explanation of a correct answer from <<Edit Quiz>> | 2 | N | Ensure that checkbox submits values | Finlay | 2
|  |  | Ensure that additional textboxes submit values | Finlay | 2
14. <<Staff>> can add an explanation of incorrect answers from <<Edit Quiz>> | 2 | N | Create additional textbox below answer textbox | Finlay | 2
|  |  | Ensure that additional textboxes submit values | Finlay | 2
15. <<Staff>> can make a quiz available to students from <<Edit Quiz>> | 1 | N | Create checkbox at top of form titled "Publish Quiz" | Finlay | 2
|  |  | Ensure that additional checkbox submits value | Finlay | 1
16. <<Staff>> can quick-access make quiz available from <<Quiz Overview>> | 1 |  |  |  | 1
17. <<Staff>> can quick-access make quiz available from <<View Individual Quiz>> | 1 |  |  |  | 1
18. <<Staff>> can quick-acess view overall results from <<View Individual Quiz>> | 1 | N | Links on quiz overview page | Dan | 1
19. <<Staff>> can sort quizzes on <<Quiz Overview>> by quizzes they have created | 2 |  |  |  | 1
|  | N | ORDER BY query to retrieve data in correct order | Dan | 1
20. <<Staff>> can see comprehensive information about a quiz from <<Quiz Summary - Staff View>> | 5 | N | Quiz summary - staff view page designed HTML/CSS | Carim | 2
|  |  | Retrieve all answers from quiz and sort into individual students + attempts | Carim | 3
|  |  | Calculate averages + totals | Carim | 2
21. <<Staff>> can filter results on <<Quiz Summary - Staff View>> by date range and/or student | 4 | N | Page: add calendar to specify date range | Aleksandr | 2
|  |  | Page: add textbox and submit button to specify student | Aleksandr | 2
|  |  | ORDER BY query to retrieve data in correct order | Aleksandr | 2
22. <<Student>> can log in using their Matriculation ID | 3 | N | Page redirection on correct credentials after login | Igors | 3
|  |  | Page redirection on incorrect credentials | Igors | 3
23. <<Student>> after logging in should be shown <<Quiz Overview>> | 1 | N | -- |  | 2
24. <<Student>> can see all modules from <<Quiz Overview>> | 2 | N | -- |  | 2
25. <<Student>> can filter quizzes by module from <<Quiz Overview>> | 1 | N | button to filter quizes, order by module | Igors | 2
|  |  | Query to get ordered list |  | 1
26. <<Student>> can filter quizzes by completion from <<Quiz Overview>> | 1 | N | Quiz overview: add checkbox to filter by completion (student permission visible only) | Igors | 2
27. <<Student>> can select a quiz listed on <<Quiz Overview>> | 1 |  |  |  | 1
28. <<View Individual Quiz>> should display a list of multiple-choice questions | 6 | N | Quiz attempt page: HTML/CSS | Jimi | 1
|  |  | Query to get each question + answer for the applicable quiz ID | Jimi | 2 | Tue: 2
|  |  | Quiz summary - student view page designed HTML/CSS | Aleksandr | 1
|  |  | Query to get explanation for each question after determining correct/incorrect | Jimi | 2
|  |  | Query to retrieve scores | Jimi | 2
|  |  | Form to add students' results to database | Jimi | 3 | bar: Wed
29. <<Student>> can print a summary from <<Quiz Summary - Student View>> | 2 | N |  | Carim | 2
CSS print stylesheets
30. <<Student>> can email a summary from <<Quiz Summary - Student View>> | 8 |  |  |  | 5
1
|  | N |  | Aleksandr | 2
HTML/CSS design email
31. <<Student>> can see a total score on <<Quiz Summary - Student View>> | 1 | N |  | Aleksandr | 2
Design to display a checkmark on quiz summary page
32. <<Quiz Summary - Student View>> should display all given answers | 1 | N |  | Aleksandr | 1
Add total score at top & bottom of quiz summary page
33. <<Quiz Summary - Student View>> should display an explanation for each correct answer where applicable | 3 | N |  | Igors | 1
after test complition student can view correct answer for each quiz
34. <<Quiz Summary - Student View>> should display an explanation for each incorrect answer where applicable | 1 | N |  | Igors | 3
after the test complition should
35. <<Student>> can see if a quiz is completed from <<Quiz Overview>> | 1 | N |  | Igors | 4
36. <<Staff>> can see all responses to a quiz on <<Quiz Summary - Staff View>> | 1 | N |  | Aleksandr | 2
Quiz overview design: add some indication of completion on overview
37. <<Staff>> can see the average score of all responses on <<Quiz Summary - Staff View>> | 1 | N |  | Aleksandr | 3
--
38. <<Student>> can favourite a module from <<Quiz Overview>> | 1 | N |  | Carim
Design to add a star icon on quiz overview page
Store preference in favourites table
39. <<Student>> can favourite a quiz from <<Quiz Overview>> | 1 | N |  | Carim
|  |  | Design to add a star icon on quiz overview page | Igor
Store preference in favourites table
40. <<Student>> can favourite a quiz from <<View Individual Quiz>> | 1 | N |  | Carim
Design to add a star icon on view quiz page
41. <<Student>> favourites should take precedence on <<Quiz Overview>> | 2 | N |  | Aleksandr
On quiz overview page, sort by favourites first
42. <<Student>> can see a summary of previously completed quizzes on <<Quiz Summary - Student View>> | 4 | N |  | Carim
|  |  | On quiz attempt page; add div at top to indicate quiz has been taken and previous results are available | Aleksandr
Link applicable summary page for each previous result