## Backlog
101 | User Story | Estimated Complexity | Tasks | Notes | Estimated Effort | Owner | Done? | Estimated Effort (Person hours) | Fri | Mon | Tue | Wed | Thu | Fri
| <<Staff>> can log in using their Staff ID | 3 | Make table for staff (users) |  | 1
|  |  | Connect to database | java mysql connector/driver | 4
|  |  | Login page designed HTML/CSS |  | 2
|  |  | Page redirection on correct credentials |  | 1
|  |  | Page redirection on incorrect credentials |  | 1
| <<Staff>> logging in should be shown <<Quiz Overview>> | 2 | Quiz overview page designed HTML/CSS |  | 3
|  |  | Quiz table connection |  | 1
| <<Staff>> can select a quiz listed on <<Quiz Overview>> | 1 | Links on quiz overview page |  | 1
| <<Staff>> can quick-access create a quiz from <<Quiz Overview>> | 1 | Links on quiz overview page |  | 1
| <<Staff>> can quick-access edit a quiz from <<Quiz Overview>> | 1 | Links on quiz overview page |  | 1
| <<Staff>> can create a quiz from <<Quiz Overview>> | 3 | Links on quiz overview page |  | 1
|  |  | Edit quiz page designed HTML/CSS |  | 4
|  |  | Permission validation |  | 1
|  |  | Check INSERT queries and integrate |  | 2
|  |  | Create question table |  | 1
|  |  | Create answers table |  | 1
| <<Staff>> can quick-access edit a quiz from <<View Individual Quiz>> | 1 | Links on quiz overview page |  | 1
| <<Staff>> can choose a module to associate with a quiz from <<Edit Quiz>> | 2 | Edit quiz page -> add dropdown box for module selection |  | 1
|  |  | Ensure that new dropdown box submits values |  | 1
| <<Staff>> can input the title of a quiz from <<Edit Quiz>> | 1 | Edit quiz page -> add textbox for title |  | 1
|  |  | Ensure that new textbox submits values |  | 1
| <<Staff>> can add questions to a quiz from <<Edit Quiz>> | 3 | Edit quiz page -> Create div that contains question name + textbox for answers |  | 1
|  |  | Ensure that all divs submit correct values |  | 1
| <<Staff>> can add multiple answers to a question from <<Edit Quiz>> | 2 | Create buttons that add additional textboxes for answers |  | 1
|  |  | Create button to add div with aforementioned functionality |  | 1
| <<Staff>> can choose which answer should be marked as correct from <<Edit Quiz>> | 3 | Create checkbox on all divs to indicate correct answer |  | 1
|  |  | Ensure that checkbox submits values |  | 1
| <<Staff>> can add an explanation of a correct answer from <<Edit Quiz>> | 2 | Ensure that checkbox submits values |  | 1
|  |  | Ensure that additional textboxes submit values |  | 1
| <<Staff>> can add an explanation of incorrect answers from <<Edit Quiz>> | 2 | Create additional textbox below answer textbox |  | 1
|  |  | Ensure that additional textboxes submit values |  | 1
| <<Staff>> can make a quiz available to students from <<Edit Quiz>> | 1 | Create checkbox at top of form titled "Publish Quiz" |  | 1
|  |  | Ensure that additional checkbox submits value |  | 1
| <<Staff>> can quick-access make quiz available from <<Quiz Overview>> | 1 | Links on quiz overview page |  | 1
| <<Staff>> can quick-access make quiz available from <<View Individual Quiz>> | 1 | Links on quiz overview page |  | 1
| <<Staff>> can quick-acess view overall results from <<View Individual Quiz>> | 1 | Links on quiz overview page |  | 1
| <<Staff>> can sort quizzes on <<Quiz Overview>> by quizzes they have created | 2 | Quiz overview page: add sort button |  | 1
|  |  | ORDER BY query to retrieve data in correct order |  | 1
| <<Staff>> can see comprehensive information about a quiz from <<Quiz Summary - Staff View>> | 5 | Quiz summary - staff view page designed HTML/CSS |  | 4
|  |  | Retrieve all answers from quiz and sort into individual students + attempts |  | 2
|  |  | Calculate averages + totals |  | 1
| <<Staff>> can filter results on <<Quiz Summary - Staff View>> by date range and/or student | 4 | Page: add calendar to specify date range |  | 2
|  |  | Page: add textbox and submit button to specify student |  | 1
|  |  | ORDER BY query to retrieve data in correct order |  | 1
| <<Student>> can log in using their Matriculation ID | 3 | Page redirection on correct credentials |  | 1
|  |  | Page redirection on incorrect credentials |  | 1
| <<Student>> after logging in should be shown <<Quiz Overview>> | 1 | -- |  | 0
| <<Student>> can see all modules from <<Quiz Overview>> | 2 | -- |  | 0
| <<Student>> can filter quizzes by module from <<Quiz Overview>> | 1 | -- |  | 0
| <<Student>> can filter quizzes by completion from <<Quiz Overview>> | 1 | Quiz overview: add checkbox to filter by completion (student permission visible only) |  | 1
| <<Student>> can select a quiz listed on <<Quiz Overview>> | 1 | -- |  | 0
| <<View Individual Quiz>> should display a list of multiple-choice questions | 3 | Quiz attempt page: HTML/CSS |  | 6
|  |  | Query to get each question + answer for the applicable quiz ID |  | 1
| <<Student>> can submit a quiz after completion on <<View Individual Quiz>> | 1 | Ensure submitted values are correct and insert into database |  | 1
| <<Quiz Summary - Student View>> should display all questions | 6 | Quiz summary - student view page designed HTML/CSS |  | 4
|  |  | Query to get each question/answer |  | 1
|  |  | Query to get explanation for each question after determining correct/incorrect |  | 1
|  |  | Query to retrieve scores |  | 1
| <<Student>> can see whether an answer is correct from <<Quiz Summary - Student View>> | 1 | Design to display a checkmark on quiz summary page |  | 1
| <<Student>> can see a total score on <<Quiz Summary - Student View>> | 1 | Add total score at top & bottom of quiz summary page |  | 1
| <<Quiz Summary - Student View>> should display all given answers | 3 | -- |  | 0
| <<Quiz Summary - Student View>> should display an explanation for each correct answer where applicable | 1 | -- |  | 0
| <<Quiz Summary - Student View>> should display an explanation for each incorrect answer where applicable | 1 | -- |  | 0
| <<Student>> can see if a quiz is completed from <<Quiz Overview>> | 1 | Quiz overview design: add some indication of completion on overview |  | 1
| <<Staff>> can see the average score of all responses on <<Quiz Summary - Staff View>> | 1 | -- |  | 0
| <<Student>> can favourite a module from <<Quiz Overview>> | 1 | Design to add a star icon on quiz overview page |  | 1
|  |  | Store preference in favourites table |  | 2
| <<Student>> can favourite a quiz from <<Quiz Overview>> | 1 | Design to add a star icon on quiz overview page |  | 2
|  |  | Store preference in favourites table |  | 1
| <<Student>> can favourite a quiz from <<View Individual Quiz>> | 1 | Design to add a star icon on view quiz page |  | 1
| <<Student>> favourites should take precedence on <<Quiz Overview>> | 2 | On quiz overview page, sort by favourites first |  | 1
| <<Student>> can see a summary of previously completed quizzes on <<Quiz Summary - Student View>> | 4 | On quiz attempt page; add div at top to indicate quiz has been taken and previous results are available |  | 2
|  |  | Link applicable summary page for each previous result |  | 1
| <<Student>> can print a summary from <<Quiz Summary - Student View>> | 2 | CSS print stylesheets |  | 3
| <<Student>> can email a summary from <<Quiz Summary - Student View>> | 8 | SMTP email server-side |  | 3
|  |  | Create email account to send results from |  | 1
|  |  | HTML/CSS design email |  | 3

## Actors
<<Student>>
<<Staff>>
<<Quiz Overview>>
<<View Individual Quiz>>
<<Edit Quiz>>